## Slide 1
Timeline | Aim 1 Increase Diversity and Inclusion | Aim 2 Foster Engagement and Collaboration | Aim 3 Expand Membership | Aim 4 Amplify virtual educational and mentorship opportunities for radiology educators and health services researchers | Aim 5 Understand , support and shape the radiology training workforce
Short-term | Determine how to systematically capture DEI metrics | Convene bi-annual meeting starting in July 2023 across / affinity groups, committees, grants and programs Revise mission and vision statements every 5 years across AUR | Create task force to study and propose a new name for AUR that is inclusive of non-university radiologists | Gather data on how trainee and staff radiologists derive value from online programs and grants | Develop 3-5 priorities that increase understanding of current and imminent factors influencing education, research and leadership in radiology training programs
Mid-term | Convene best practices in DEI Create guidelines on faculty diversity Update DEI metrics as needed to adapt to evolving organizational goals | Align mission and vision statements across AUR Identify at least 2 areas for collaboration across at least 3 groups / committees (focus on educator education, mentorship and HSR) Increase meaningful social media engagement | Gather and disseminate quantitative and qualitative data on why and on how / why AUR is valuable to members Make annual meeting more affordable for all trainees, | Disseminate data on value of online content and grants Gather data (on how / why mentorship is valuable to members | Gather quantitative and qualitative data on factors influencing radiology training workforce using the 3-5 priorities Present common themes, pressure points and best practices from qualitative and quantitative research to membership and leadership
Long-term (TENTATIVE) | Increase the diversity of AUR members, committee members and annual meeting speakers Correlates DEI data with direct benefit to AUR. This Aim will guide the next strategic plan. | Establish a diverse outreach task to strengthen cohesion across AUR, cultivate relationships with other societies and international chapters, and partner with organizations to build content (educator education, mentorship and HSR) that can be leveraged across multiple meeting venues. | Disseminate data from mid-term goals Aim to members Develop one intervention that draws on findings from mid-term goal data in order to increase membership and improve member satisfaction. This Aim will guide the next strategic plan. | Use data from short-term goal to define metrics and best practices for online content engagement and grant submission. Create formal benchmarks, guidelines and best practices in mentorship by December 2025 | Develop an intervention that can demonstrate a measurable change in education, research and leadership in radiology training programs based on findings from the short and medium-term deliverables. These goals will guide the next strategic plan.

## Slide 2
Timeline | Aim 1 Increase Diversity and Inclusion | Aim 2 Foster Engagement and Collaboration | Aim 3 Expand Membership | Aim 4 Amplify virtual educational and mentorship opportunities for radiology educators and health services researchers | Aim 5 Understand , support and shape the radiology training workforce
Short-term | The DEI committee will determine how to systematically capture DEI metrics and leverage this data for societal diversity efforts by June 2023. Ideal metrics will be submitted to the new management company by May 2023 in order to be incorporated into new member build out. | LRP will convene a bi-annual meeting starting in July 2023 across SIG / affinity groups, committees, grants and programs. This forum will create a space for these parties to begin to identify the value of AUR, best practices and barriers / facilitators for collaboration. These data will be stored on an AUR accessible website. AUR mission and vision statements will be revised every 5 years, starting in April 2024, using 2022 SWOT. Affinity / SIG groups, Committees, grants and programs will review and revise individual mission and vision statements by April 2024 LRP will facilitate alignment of mission and vision statements across SIG / affinity groups, committees, grants and programs AUR Education committee, RAHSR and grants programs by December 2024 | EC and BOD will create a stakeholder task force, including trainees and hybrid / private practice radiologists, to study and propose a new name for AUR that is inclusive of non-university radiologists by December 2023 (Also supports Aims 1 and 2) | AUR Education committee, RAHSR and grants programs will gather data on how trainee and staff radiologists derive value from online programs and grants (e.g. top content, optimal format, best practices) by December 2023. Include insights from AUR members with other society memberships (e.g. ARSS) Create database of best practices Understand how to improve the quality of grant submissions | LRP work with Affinity / SIG groups, Well Being committee leaders, APDR, APCR and APDIR to develop 3-5 priority open ended questions / themes that increase understanding of current and imminent factors influencing education, research and leadership in radiology training programs by December 2024 This data can be gathered in collaboration with other societies (e.g. leadership with ACR, APC, APDIR).

## Slide 3
Timeline | Aim 1 Increase Diversity and Inclusion | Aim 2 Foster Engagement and Collaboration | Aim 3 Expand Membership | Aim 4 Amplify virtual educational and mentorship opportunities for radiology educators and health services researchers | Aim 5 Understand , support and shape the radiology training workforce
Mid-term | DEI committee will convene best practices in DEI from across affinity and sig groups members by January 2024 Program planning committee and BOD will create guidelines on faculty diversity resulting in 20% new annual meeting faculty by January 2024. Share this data with AUR members each January. The % of new faculty will be increased annually. (Also supports Aims 2,3, and 4) Update DEI metrics as needed to adapt to evolving organizational goals | LRP will facilitate alignment of mission and vision statements across SIG / affinity groups, committees, grants and programs AUR Education committee, RAHSR and grants programs by December 2024 By April 2024 Affinity / SIG groups, Committees, grants and programs will use data on how / why AUR is valuable and barriers / facilitation to collaboration to identify at least 2 areas for collaboration across at least 3 groups / committees (focus on educator education, mentorship and HSR) Electronic Communications committee will increase meaningful social media engagement by increasing followers to 5k by December 2023, phased increase communication frequency to 2x week by July 2024 and creating new targeting teaching tip content. (Supports Aims 3 and 4) | Membership committee will gather and disseminate quantitative and qualitative data on why and on how / why AUR is valuable to members by 2024 annual meeting using a phased approach (e.g. stories on why members joined/ stayed / left). (Also supports Aim 2) Finance committee will determine how to make annual meeting more affordable for all trainees, including non-chief residents, (e.g. reduced meeting fees, expand travel stipends) by March 2024 | AUR Education committee, RAHSR and grants programs will disseminate data on value of online content and grants to SIG / affinity groups, program planning committee and membership by April 2024 . Education committee (???) will work with new management company to gather data (on how / why mentorship is valuable to members by December 2024. This will ideally be done using semi- structured approaches drawing from other societies and institutions.. | LRP, Affinity / SIG groups, Well Being committee leaders, APDR, APCR, APDIR and new management company to gather quantitative and qualitative data on factors influencing radiology training workforce using the 3-5 priorities outlined in short-term goals by June 2024. Affinity / SIG groups, Well Being committee leaders, APDR, APCR and APDIR will present common themes, pressure points and best practices from qualitative and quantitative research to membership and leadership by April 2025 at annual meeting and through e-mail as well as social media.

## Slide 4
Timeline | Aim 1 Increase Diversity and Inclusion | Aim 2 Foster Engagement and Collaboration | Aim 3 Expand Membership | Aim 4 Amplify educational opportunities for radiology educators and health services researchers | Aim 5 Understand , support and shape the academic radiology workforce
Long-term | TENTATIVE Increase the diversity (e.g. age, race, gender, geography, program type) of AUR members by 10% and of committee members and annual meeting speakers by 20% by June 2026. DEI committee will develop one measurable outcome by June 2025 that correlates DEI data with direct benefit to AUR. This measure will be integrated into next strategic plan | TENTATIVE BOD will establish a diverse outreach task force of members from across the SIG / affinity groups, committees, grants and programs tasked with strengthen cohesion across these groups. This task force will also cultivate relationships with other societies and international chapters, and partner with organizations with a goal to build content (educator education, mentorship and HSR) that can be leveraged across multiple meeting venues by July 2026. | TENTATIVE Membership committees will disseminate data from mid-term goals Aim with members (e.g. social media, online, in person), by June 2025 Membership and Affinity and Special Interest Group leaders to develop one intervention by March 2025 that draws on findings from mid-term goal data in order to increase membership and improve member satisfaction, each by 20%. This Aim will guide the next strategic plan. | TENTATIVE AUR Education committee, RAHSR and grants programs will use data from short-term goal to define metrics and best practices for online content engagement and grant submission that increases engagement, quality of grant submissions and perceived value by 25% (metrics TBD from ST goal) by June 2025. ? Will create formal benchmarks, guidelines and best practices in mentorship by December 2025 | TENTATIVE LRP, Affinity / SIG groups, Well Being committee leaders, APDR, APCR and APDIR will develop an intervention that can demonstrate a measurable change in education, research and leadership in radiology training programs by December 2025. Details of the metric and target group will be directed by findings from the short and medium-term deliverables. These goals should be measured by December 2026 and will guide the next strategic plan.